## Sheet1
Control ID | Control Title | Requirement Summary | Current Status | Owner | Action Needed | Target Date
A.5.1 | Information Security Policies | Policies approved,published,review annually | Partially Implemented | CISO | Draft and approve info sec policy | Q3 2026
A.5.2 | Segregation of Duties | Conflicting duties separated | Not implemented | CTO | Map roles and split admin/dev access | Q2 2026
A.6.5 | Access Control | Users register/de-register access | Implemented | IT Manager | Maintain Monthly Review | N/A
A.7.4 | Physical Security Monitoring | Premises Monitored(CCTV, Alarms) | Implemented | N/A | Document as out of scope | Done
A.8.1 | Asset Inventory | All assets listed and owned | Partially Implemented | IT Manager | Complete asset inventory | Q2 2026
A.8.7 | Removable Media | Restriciton on USB drives | Not implemented | IT Manager | Create Policy & disable USB ports | Q3 2026
A.8.8 | Equipment Security | Secure disposal of equipment | Planned | IT Manager | Create Secure disposal procedure | Q4 2026
A.8.9 | Clear desk& screen | Lock screens when away | Partially Implemented | HR | Company Wide Training + Monthly spot | Q3 2026
A.9.4 | Password Management | Password Policy | Implemented | CISO | Verify every 6 months | Ongoing
A.9.5 | Multi-factor authentication | MFA for remote access | Implemented | CISO | Enforce on all Saas apps | Done
A.12.1 | Operational Procedures | Documented Change Management | Not implemented | CTO | Create change Control Process | Q2 2026
A.12.4 | Logging & Monitoring | Audit logs Enabled,Reviewed | Partially Implemented | Devops | Enable CloudTrail + Weekly log review | Q2 2026
A.12.6 | Technical Vulnerability Management | Regular scans & patching | Planned | Devops | Schedule Monthly Vulnerability scans | Q2 2026
A.13.1 | Network controls | Firewalls,segmentation | Implemented | Devops | Review quarterly | Ongoing
A.16.1 | Incident Management | Incident Response plan | Planned | CISO | Draft IR Plan | Q3 2026